# Pharmacy Delivery: Weekly Status

## Current Status

Status: On track. On time delivery rate is 95 percent across three pilot clinics.

The pilot expanded to the South clinic this week.

## Decisions

Decision: MedDash replaces SwiftRoute as the courier partner after a pricing review.

Decision: Delivery window set to 2 to 6 PM.

## Blockers

Blocker: Address validation fails for about 6 percent of member records.

## Next Steps

Next: The team plans to run a member satisfaction survey in week 3.

Next: Clean member address data with the data team.